## Team1_Estimated_Effort
Task Name: (Dependencies top to bottom) | [8 empty] | Munia | Fiza | DaVon | Mariam | Harold | Cole
|  |  | Role | Owner | Estimated | Effort | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual
|  |  |  | (primary owner) (secondary owners) | By Task | Subtotals | By Task | Subtotals | By Task | By Task | By Task | By Task | By Task | By Task
Preliminary &
Parallel Tasks | Architecture |  |  |  |  | 8 |  | 3
|  | Design architecture | Project Manager | Munia, Fiza | 8 |  | 3 |  | 2 | 0 |  |  |  |  | 2
| Requirements |  |  |  |  | 7 |  | 6 | [6 empty] | 0
|  | Gather | Requirements Engineer | Mariam, Fiza | 2 |  | 2 |  | 2 | 1 |  |  |  |  | 3
|  | Analyze | Requirements Engineer | Fiza, Mariam | 3 |  | 2 |  | 2 | 1 |  |  |  |  | 3
|  | Specify | Requirements Engineer | DaVon | 2 |  | 2 |  | 1 | 2 |  |  |  |  | 3
| Documentation |  |  |  |  | 29 |  | 42 | [6 empty] | 0
|  | Project Charter | Project Manager | Munia, Fiza, Mariam | 3 |  | 2 |  | 0 | 3 |  |  |  |  | 3
|  | Release Plan | Project Manager | Munia | 2 |  | 4 |  | 0.5 | 3 |  |  |  |  | 3.5
|  | Requirements Document | Project Manager, Requirements Engineer | Mariam, Fiza | 4 |  | 7.5 |  | 0.5 | 6 |  |  |  |  | 6.5
|  | Project Plan | Project Manager, Developers | All | 6 |  | 10.5 |  | 0 | 6 |  | 2 | 2 | 2 | 12
|  | Architecture Document | Architect | Harold | 3 |  | 5 |  | 2 | 2 |  |  |  |  | 5
|  | Test Report | Tester | Cole, Harold | 8 |  | 6 |  | 1 | 6 |  |  |  |  | 7
|  | User Guide & System Admin Doc | Developers, Requirements Engineer | All | 3 |  | 7 |  | 0.5 | 5 |  | 1 | 1 | 1 | 8.5
Coding | [6 empty] | 0 | [7 empty] | 0
Iteration 1: | Development |  |  |  |  | 61 |  | 156 | [6 empty] | 0
|  | Determine technology needs | Developer | Munia | 1 |  | 4 |  |  |  | 1 | 1 | 1 | 1 | 4
|  | Research and learn new language and environment | Developer | Munia | 20 |  | 50 |  | 1 |  | 22 | 9 | 9 | 9 | 50
|  | Set up proxy server software | Developer | Cole | 8 |  | 5 |  | 5 | [5 empty] | 5
|  | Write basic proxy code | Developer | Cole | 5 |  | 10 |  | 10 | [5 empty] | 10
|  | Implement classes | Developer | DaVon , Harold | 10 |  | 36 |  |  |  |  | 12 | 12 | 12 | 36
|  | Create HTTP handling code | Developer | DaVon | 8 |  | 15 |  |  |  |  | 5 | 5 | 5 | 15
|  | Write code to store user name locally | Developer | Mariam, Cole | 2 |  | 24 |  |  |  |  | 8 | 8 | 8 | 24
|  | Write code for managing HTTP session | Developer | Fiza, Munia, Harold | 5 |  | 12 |  |  |  |  | 4 | 4 | 4 | 12
|  | Unit Testing | Developer | Cole,DaVon | 2 |  | 0 | [7 empty] | 0
| Analysis |  |  |  |  | 6 |  | 7 | [6 empty] | 0
|  | System Testing | Tester | Cole, DaVon | 2 |  | 2 |  | 1 | 1 |  |  |  |  | 2
|  | Bug fix as required | Tester, Developer | Cole, Fiza, Mariam, DaVon | 2 |  | 3 |  |  |  |  | 1 | 1 | 1 | 3
|  | Evaluate needs for next iteration | Project Manager | Cole, Mariam | 2 |  | 2 |  | 1 | 1 |  |  |  |  | 2
Iteration 2: | Design |  |  |  |  | 12 |  | 7.8 | [6 empty] | 0
|  | Implement any design changes | Project Manager | ALL | 2 |  | 0.5 |  | 0.5 | [5 empty] | 0.5
|  | Risk analysis | Project Manager | Fiza, Harold, Von | 2 |  | 1 |  | 0.5 | 0.5 |  |  |  |  | 1
|  | Design XML format | Developer | ALL | 1 |  | 0.3 |  |  |  |  | 0.1 | 0.1 | 0.1 | 0.3
|  | Design Perl XML-handling code | Developer | ALL | 5 |  | 0 | [7 empty] | 0
|  | Create UI design for balance screen | Developer | ALL | 2 |  | 6 |  |  |  |  | 2 | 2 | 2 | 6
| Development |  |  |  |  | 22 |  | 16 | [6 empty] | 0
|  | Review requirements | Developer | Mariam, Fiza | 1 |  | 3.5 |  |  |  | 0.5 | 1 | 1 | 1 | 3.5
|  | Create XML parsing code | Developer | ALL | 5 |  | 1 |  |  |  | 1 |  |  |  | 1
|  | Handle XML data structure for retrieving balance | Developer | ALL | 10 |  | 5 |  | 3 |  | 2 |  |  |  | 5
|  | Implement UI | Developer | ALL | 4 |  | 6 |  |  |  | 2 | 4 | 2 | 4 | 12
|  | Unit Testing | Developer | Cole, Von | 2 |  | 0.5 |  |  |  | 0.5 |  |  |  | 0.5
| Analysis |  |  |  |  | 6 |  | 7.5 | [6 empty] | 0
|  | System Testing | Tester | Cole, Von | 2 |  | 1.5 |  | 0.5 | 1 |  |  |  |  | 1.5
|  | Bug fix as required | Tester, Developer | Munia, Harold Mariam | 2 |  | 5.5 |  | 0.5 |  | 2 | 1 | 1 | 1 | 5.5
|  | Evaluate needs for next iteration | Project Manager | Mariam, Fiza | 2 |  | 0.5 |  | 0.5 | [5 empty] | 0.5
Iteration 3: | Design |  |  |  |  | 13 |  | 11.45 | [6 empty] | 0
|  | Implement any design changes | Project Manager | Munia, Fiza | 2 |  | 0.45 |  | 0.25 | 0.2 |  |  |  |  | 0.45
|  | Risk analysis | Project Manager | Mariam, Fiza | 2 |  | 1 |  | 0.5 | 0.5 |  |  |  |  | 1
|  | Create UI design for vendor locations | Developer | Cole, Harold | 5 |  | 9 |  |  |  |  | 3 | 3 | 3 | 9
|  | Design data structure for RSS location list | Developer | Von, Fiza | 4 |  | 1 |  |  | 0.5 | 0.5 |  |  |  | 1
| Development |  |  |  |  | 22 |  | 23 | [6 empty] | 0
|  | Review requirements | Developer | ALL | 1 |  | 1 |  | 0.1 | 0.1 | 0.2 | 0.1 | 0.2 | 0.3 | 1
|  | Develop code for processing vendor locations | Developer | ALL | 7 |  | 8 |  | 0.5 | 1 | 2 | 0.5 | 2 | 2 | 8
|  | Implement vendor map display | Developer | ALL | 6 |  | 8 |  |  |  | 2.5 |  | 2.5 | 3 | 8
|  | Display vendor information | Developer | ALL | 6 |  | 4 | [5 empty] | 2 | 2 | 4
|  | Unit Testing | Developer | Cole, Von | 2 |  | 2 |  |  |  |  | 1 |  | 1 | 2
| Analysis |  |  |  |  | 4 |  | 2 | [6 empty] | 0
|  | Acceptance Testing | Tester, Project Manager | Harold, Munia | 2 |  | 1 |  | 0.5 |  |  |  | 0.5 |  | 1
|  | Bug fix as required | Tester, Developer | ALL | 2 |  | 1 |  | 0.3 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 1
Coding | [6 empty] | 0 | [7 empty] | 0
Iteration 4: | Development |  |  |  |  | 48 |  | 156 | [6 empty] | 0
|  | Fix delays in local hosting interface | Developer | Munia | 1 |  | 4 |  |  |  | 1 | 1 | 1 | 1 | 4
|  | Fix client-side UX bugs | Developer | Munia | 10 |  | 50 |  | 1 |  | 22 | 9 | 9 | 9 | 50
|  | Develop user feedback system | Developer | Cole | 8 |  | 5 |  | 5 | [5 empty] | 5
|  | Encrypt user information | Developer | Cole | 4 |  | 10 |  | 10 | [5 empty] | 10
|  | Implement classes | Developer | DaVon , Harold | 5 |  | 36 |  |  |  |  | 12 | 12 | 12 | 36
|  | Create HTTP handling code | Developer | DaVon, Munia | 3 |  | 15 |  |  |  |  | 5 | 5 | 5 | 15
|  | Complete login page | Developer | Mariam, Cole | 2 |  | 24 |  |  |  |  | 8 | 8 | 8 | 24
|  | Set up notification page | Developer | Fiza, Munia, Harold | 5 |  | 12 |  |  |  |  | 4 | 4 | 4 | 12
|  | Set up Transaction page | Developer | Harold, Fiza, Mariam | 8
|  | Unit Testing | Developer | Cole,DaVon | 2 |  | 0 | [7 empty] | 0
| Analysis |  |  |  |  | 4 |  | 7 | [6 empty] | 0
|  | System Testing | Tester | Cole, DaVon | 2 |  | 2 |  | 1 | 1 |  |  |  |  | 2
|  | Bug fix as required | Tester, Developer | Cole, Fiza, Mariam, DaVon | 1 |  | 3 |  |  |  |  | 1 | 1 | 1 | 3
|  | Evaluate needs for next iteration | Project Manager | Cole, Mariam | 1 |  | 2 |  | 1 | 1 |  |  |  |  | 2
Total |  |  |  |  | 190 | 190 | 292.25 | 281.75 | 37.15 | 41 | 36.4 | 55.8 | 59.4 | 62.5 | 292.25